Action Plan – April 2015 to August 2016

Citizens for Educational Excellence - ESC Region 2

Date of Action Plan submitted to UNT -  July 22, 2015

Members of Partnership (Please list all)

| Name (include yourself) | District/University/Workforce or P-16 Council | Title/Position | Email | Phone |
| --- | --- | --- | --- | --- |
| Dr. Janet Cunningham | Education to Employment Partners (P-16 Council) | Executive Director | jcunningham@edexcellence.org | 361-242-5980 |
| Toni Norrell | ESC Region 2 | Math Curriculum Consultant | Toni.norrell@esc2.us | 361-561-8572 |
| Melissa Morin | ESC Region 2 | Human Resources Director | Melissa.morin@esc2.us | 361-561-8416 |
| Paul Johnson | Del Mar College | Math Instructor | pjohnson@delmar.edu | 361-698-1468 |
| Kathy Cuyler | Coastal Bend College | Math Division Chair | kcuyler@coastalbend.edu | 361-354-2428 |
| Paula Kenney-Wallace | Texas A&M-Corpus Christi | Math Instructor | Paula-kenney-wallace@tamucc.edu | 361-852-6028 |
| Jose Guerra | Texas A&M -Kingsville | Math Coordinator | Jose.guerra@tamuk.edu | 361-593-2113 |
| Polly Allred | Texas A&M-Kingsville | Math Instructor | Polly-allred@tamuk.edu | 361-593-3519 |
| Dr. Melana Silva | Calallen ISD | Curriculum Specialist | msilva@calallen.org | 361-242-5600 |
| Sandra Rippstein | Calallen ISD | Secondary Teacher | srippstein@calallen.org | 361-242-5626 |
| Carlos Guerrero | Robstown ISD | Instructional Coach | Carlos.guerrero@robstownisd.org | 361-767-6600 |
| Jake Salcines | Robstown ISD | District Specialist | Jake.salcines@robstownisd.org | 361-767-6600 |
| Dr. Veronica Gutierrez | Odem-Edroy ISD | District Administrator | vgutierrez@oeisd.org | 361-368-8121 |
| Lisa Hernandez | Odem-Edroy ISD | Math Teacher | hernandezl@oeisd.org | 361-368-8121 |
| Cindy Funke | Odem-Edroy ISD | Math Teacher | funkec@oeisd.org | 361-368-8121 |
| Joe Flores | Odem-Edroy ISD | Math Teacher | floresj@oeisd.org | 361-368-8121 |
| Shere Salinas | Corpus Christi ISD | Math Specialist | Shere.salinas@ccisd.us | 361-695-7200 |
| Marc Aguilera | Corpus Christi ISD | Math Specialist | Marcos.aguilera@ccisd.us | 361-695-7200 |

Goals of partnership

- Develop and sustain partnerships with 6 ISDs, 4 post-secondary institutions, ESC 2, and Workforce Solutions to facilitate providing information about career endorsements to students, counselors and teachers.

- Continue to develop, offer, document, and analyze results of the College Preparatory Courses (CPCs).

- Deepen vertical alignment of the Mathematics offerings of ISDs and post-secondary partners, including non-course based options.

Objectives supporting your goals

1. Students, counselors, and teachers will have a greater understanding of the five endorsements and the career pathways to those endorsements.

2. The number of students taking College Preparatory Courses will increase by 10%.

3. Secondary mathematics teachers and postsecondary instructors will utilize various opportunities to discuss and vertically align courses.

Plan of Work

| # of Related Objective(s) Above | Activity | Planned Evidence of Implementation | Planned Evidence of Impact |
| --- | --- | --- | --- |
| #1 | Increase the number of partnerships and develop team relationships | Attendance at meetings, agendas, minutes | Planning of future events. |
| #1 | Development of Ready for College and Career Conference for Counselors | Program, presentation materials, evaluations | Qualitative and quantitative data on evaluations forms; utilizing materials in the school setting |
| #1 | Development of Exploring Endorsements Conference for Grades 8, 9, 10 | Program, presentation materials, evaluations | Selection of endorsements by students; qualitative and quantitative data regarding conference |
| #2 | Strengthen MOUs to include data gathering | Agendas, meeting minutes | MOU revision |
| #2 | Utilize CPC results to determine effectiveness | Gather data; analyze | Report for AVATAR Team |
| #3 | Promote student success through conversations and actions focused on vertical alignment | Agendas, meeting minutes | Strengthening of CPC course, exams, and daily instruction. |
| #3 | Improve vertical alignment by hosting a mathematics symposium | Program, presentation materials, evaluations | Qualitative and quantitative data regarding conference |
| #3 | Provide externship opportunities for mathematics teachers with local businesses | Assignments, timesheets, lesson plans | Lesson plans utilizing real world math |

Timeline, Responsibility, Resources, and Evaluation

| Date | Activity | Who is Responsible | Resources Needed | Associated Evaluation |
| --- | --- | --- | --- | --- |
| Sept. 30, 2015 | Increase the number of partnerships and develop team relationships | AVATAR Team | AVATAR materials | Qualitative assessment |
| October 30, 2015 | Development of Ready for College and Career Conference for Counselors | E2E Director | Program, speakers, venue, general materials | Post-event survey |
| Feb. 27, 2016 | Development of Exploring Endorsements Conference for Grades 8, 9, 10 | ESC Director | Program, speakers, venue, general materials | Post-event survey |
| June 30, 2016 | Strengthen MOUs to include data gathering | ESC Director | Current MOU and related documents | Revised MOU |
| June 30, 2016 | Utilize CPC results to determine effectiveness | ESC Research Analyst | CPC results | Possible revision of topics or assessment questions |
| June 30, 2016 | Promote student success through conversations and actions focused on vertical alignment | E2E Director | AVATAR materials | Student course data |
| Nov. 30, 2015 | Improve vertical alignment by hosting a mathematics symposium | E2E Director | Program, speakers, venue, general materials | Post-event survey |
| July 31, 2016 | Provide externship opportunities for mathematics teachers with local businesses | Workforce Director | Funding for stipends, employers willing to assist, general materials | Post-event survey; lesson plan documentation |

Budget plan

| Anticipated activity | Personnel cost/Stipends | Travel | Materials/Supplies | Food | Consultant |  |
| --- | --- | --- | --- | --- | --- | --- |
| 8 VAT (AVATAR meetings) | $5,000 |  | $100 | $200 |  |  |
| 3 conferences |  | $300 | $1900 | $1,000 |  |  |
| TOTAL | $5,000 | $300 | $2,000 | $1,200 |  |  |