| Date | Vertical Alignment Actions | Resources Required and Persons Responsible | Evidence of Implementation | Evidence of Impact |
| --- | --- | --- | --- | --- |
|  | Forming and Sustaining Vertical Alignment Partnerships and Course Team Relationships |  |  |  |
| September 10, 2012 | Convene Vertical Alignment Partners | Coordinator/Facilitator – R. Shaeffer | Products: - Meeting/Session Documentation Form - AVATAR Meeting Minutes - AVATAR Meeting Participant List Action Items: - Group norms established and communicated - Format for meeting established – online & face to face - Developed process for meeting evaluation - Recorded minutes - Distributed meeting minutes after meeting - Meeting/session documentation form completed with agreed upon action items and deadlines for completion | Forming and Sustaining Vertical Alignment Partnerships in Region |
|  | Promoting Student Success through Critical Conversations, Actions, and Outcomes to Promote Student Success |  |  |  |
| September 24, 2012 | Regional Action Plan for 2012-2013 Due | Coordinator/Facilitator – R. Shaeffer | Products: - Regional Action Plan for 2012-2013 Action Items: - Developed plan for implementation - Present Regional Action Plan for collaboration at meeting on _______________. | Forming and Sustaining Vertical Alignment Partnerships in Region |
| May 24, 2013 | Regional Sustainability Plan for 2013-2014 Due | Coordinator/Facilitator – R. Shaeffer | Products: - Regional Sustainability Plan for 2013-2014 Action Items: - Developed plan for sustainability | Sustaining Vertical Alignment Partnerships in Region |
|  | Collecting and Reporting Regional Student Data |  |  |  |
| September 17, 2012 | Development and Approval of Regional PowerPoint Due | Coordinator/Facilitator – R. Shaeffer P-16 Council Coordinator – J. McCormick/C. Villafranco | Products: - Regional Data - Regional PowerPoint Action Items: - Submit completed Regional PowerPoint - Present Regional PowerPoint data to partners at meeting on _______________ | Creating Shared Understandings and Foundations |
|  | Creating Shared Student College and Career Readiness and Success Understandings and Foundations |  |  |  |
| January 7, 2013 | Convene Vertical Alignment Partners, Secondary and Postsecondary Administrators, and P-16 Council Members for Progress Update | Coordinator/Facilitator – R. Shaeffer | Products: - Meeting/Session Documentation Form - AVATAR Meeting Minutes - AVATAR Meeting Participant List Action Items: - Progress Update Meeting with Vertical Alignment Partners, Secondary and Postsecondary Administrators, and P-16 Council Members | Creating Shared Understandings and Foundations |
| May 24, 2013 | Convene Vertical Alignment Partners, Secondary and Postsecondary Administrators, and P-16 Council Members for Progress Update | Coordinator/Facilitator – R. Shaeffer | Products: - Meeting/Session Documentation Form - AVATAR Meeting Minutes - AVATAR Meeting Participant List Action Items: - Progress Update Meeting with Vertical Alignment Partners, Secondary and Postsecondary Administrators, and P-16 Council Members | Creating Shared Understandings and Foundations |
|  | Training 2012-2013 Vertical Alignment Course Team |  |  |  |
| September 17, 2012 | Identify Team Members | Coordinator/Facilitator – R. Shaeffer | Products: - VAT training team members list - Communication with VAT supervisors - VAT roles and responsibilities documentation and training - Training agenda - Participant sign-in sheet - Training follow-up dates Action Items: - Training follow-up dates - Determine training location, date, time - Create training agenda - Notify Team Members and Supervisors - Communicate Roles and Responsibilities | Forming and Sustaining Vertical Alignment Partnerships in Region |
| October 8, 2012 | Documentation of Training | Coordinator/Facilitator – R. Shaeffer | Products: - VAT training team members list - Communication with VAT supervisors - VAT roles and responsibilities documentation and training - Training agenda - Participant sign-in sheet - Training follow-up dates Action Items: - Training follow-up dates | Forming and Sustaining Vertical Alignment Partnerships in Region |
| Start by Oct. 15, 2012 | Reviewing Course Syllabi and Reference Course Profile Information |  |  |  |
| January 10, 2013 | Document Review of Course Profile Information | Coordinator/Facilitator – R. Shaeffer Post-Secondary Partners C. Krueger J. Kulhanek | Products: - Course Profile Action Items: - Review Course Syllabi - Develop Regional Course Profile for course | Promote Student Success through Critical Conversations, Action and Outcomes |
|  | Training 2013-2014 Course Team and Sustaining the Regional Partnership and Vertical Alignment Work |  |  |  |
| On or before May 24, 2013 | Hold Training for 2013-14 Vertical Alignment Course Team (Vertical alignment agreement completed) | Coordinator/Facilitator – R. Shaeffer P-16 Council Coordinator – J. McCormick/C. Villafranco | Partnership Created and Training Conducted and Documented | Sustaining Vertical Alignment Partnerships in Region |
| On or before May 24, 2013 | Conduct Regional Vertical Alignment Partners’ Reflections, Celebrations and Next Steps 2013-2014. | Coordinator/Facilitator – R. Shaeffer P-16 Council Coordinator – J. McCormick/C. Villafranco | Meeting Held and Actions’ Documented | Sustaining Vertical Alignment Partnerships in Region |
|  | Outreaching and Communicating Your Regional Work with Education System Administrators, Key Leaders, P-16 Council Members, and Others |  |  |  |
| Monthly | Partners and Team Members Vertical Alignment Outreach Activities and Outcome Logs and Meeting/Sessions Forms Completed and Submitted | Coordinator/Facilitator – R. Shaeffer P-16 Council Coordinator – J. McCormick/C. Villafranco | Products: - P-16 Council Meeting Dates includes AVATAR report - P-16 Council Meeting Minutes include AVATAR report - Partnership leaders Meeting Dates include AVATAR report - Partnership leaders Meeting Minutes include AVATAR report Action Items: - Request time on agenda for P-16 Council Meetings - Request time on agenda for Partnership leaders meetings | Sustaining Vertical Alignment Partnerships in Region |