Action and Sustainability Plan – August 2012 to July 2013

(see Items for Consideration)

Region:  	6

| Date | Vertical Alignment Actions | Resources Required and Persons Responsible | Evidence of Implementation | Evidence of Impact |
| --- | --- | --- | --- | --- |
|  | Regional Data Collection, Reporting, Use in Decision Making, and Follow Up1 |  |  |  |
| August 13, 2012 | Trainer of trainers – AVATAR overview and commitments | Partners | Discussed and set team focus | Selected English as discipline and will focus on freshman composition; set next meeting for 9/10/12 |
|  | Partnership Goals Related to Critical Conversations, Actions, and Outcomes for Students’ Success2 |  |  |  |
| September 10, 2012 | Determine partners, review reference course profile for Composition I, choose data sources, assign roles | Partners | Discussed and assigned roles for October 8 meeting | Outcomes reported at the May 24, 2013 Reflections, Celebrations, and Next Step meeting |
| October 8, 2012 | Discuss and submit regional data powerpoint | Partners | Powerpoint submitted | Data used to determine additional partners |
|  | Course Syllabi and Reference Course Profile Information Review3 |  |  |  |
| October 8, 2012 | Compare Eng 1301 and 1302 syllabi with TEKS, EOC, and CCRS requirements | Partners | Discussed, will include high school teachers at November 5 meeting | Decision to include high school teachers |
|  | Shared Understandings/Foundations |  |  |  |
| November 8, 2012 | Discuss perceptions of “college ready” with high school teachers and college instructors | Partners | Sign-in sheet, minutes | Ongoing – shared understandings between high school and college expectations |
|  | Creating and Training 2013-2014 Vertical Alignment Team |  |  |  |
| On or before May 1, 2013 | Hold training for 2013-14 Vertical Alignment Team | P-16 Council Leader and AVATAR Coordinator/ Facilitator | Team to meet before August 2013 | Sustaining vertical alignment partnerships in region |

Items to Consider in Developing Your AVATAR Regional Vertical Alignment Action and Sustainability Plans for August 2012 to July 2013:

Partner and Team Relationships: Norms, Logistics, Expectations, and Documentation

- Setting meeting dates, times, locations, agendas, refreshments, session format (on-line, face to face, or blended)

- Attendance records, meeting minutes, and follow up items (Please use AVATAR Meeting and Documentation Form)

- Are other partners or team members needed? Who?

- Are there ways to support the team members and partners in conducting their work?

1Regional Data Collection, Reporting, Use in Decision Making, and Follow Up

- What sources will be used to gather data?

- What benchmarks are relevant?

- Use data to benchmark regional student college and career readiness and success

- Use data to sustain and develop regional course alignment efforts

- Use data to sustain and develop regional course alignment efforts

Shared Understanding of College and Career Readiness Standards and Assessments among Educational Partners and Team Members

- What do we know about CCRS and student success?

- What do we need to know to create a shared foundation for vertical alignment work?

2Partnership Goals Related to Critical Conversations, Action, and Outcomes for Students’ Success

Ideas to consider in prioritizing goals (modified from Conley 2010):

- Create and maintain regional college-going and completion cultures;

- Create and deliver core academic programs leading to college and career success (consider disciplines);

- Teach and expect student self-responsibility and management;

- Make academic “real” with opportunities for work applications;

- Align grading, assignments, and educational practices among educational systems;

- Engage educational leaders in developing, implementing, and evaluating regional priorities/actions;

- Engage in regional career readiness and employment continuous improvement planning

Course Syllabi and Reference Course Profile Information Review

Ideas to consider (modified from THECB 2012 and Conley 2011):

Regional College and Career Readiness related to:

- Content knowledge;

- Cognitive strategies;

- Learning skills and techniques; and

- Transitions between educational systems

- What course(s) will be reviewed and why?

Communications with Vertical Alignment Partners and Team Members Regarding Critical Conversations, Progress, Outcomes, and Outreach Efforts

- P-16 Council Meeting dates and minutes reflecting AVATAR reports presented;

- Partnership leaders/administrators meeting dates and minutes reflecting AVATAR reports presented;

- Presentations at local, regional, state, and national meetings; and

- Articles, newsletters, reports, etc. where information about regional vertical alignment is shared

Sustainability of Regional Vertical Alignment Partnership and Work

- Select courses for 2013-2014 vertical alignment team

- Select team members for 2013-2014 vertical alignment team

- Train 2013-2014 course alignment team