UTPA_STC_PSJA Science Vertical Alignment Action Plan

2012-2013 Target Content: Science (Chemistry and Physics)

| Action | What | When | Where | How | Who | Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Participate in VAT training |  |  |  |  |  |
|  | Attend AVATAR Partner Training | 8/13/12 | Fort Worth | Participation in training | Laura Saenz-UTPA Cindy Valdez-UTPA Wally Johnson-STC Tina McIntyre-Reg I David Garza-PSJA Luis Suarez-PSJA | Introductory knowledge acquired |
|  | AVATAR Video Conference | 8/28/12 | Region One |  | Laura Saenz-UTPA Cindy Valdez-UTPA Barbara Gonzalez-Reg I Daniel Plas-UTPA | Clarification of timeline and expectations for AVATAR |
| 2. | Form and sustain partnerships |  |  |  |  |  |
|  | Partner meeting | 10/26/12 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Cindy Valdez-UTPA Daniel Plas-UTPA David Garza-PSJA Wally Johnson-STC Ludy Avila-STC | Initial meeting held |
|  | Partner meeting | 11/9/12 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA David Garza-PSJA Israel Nicanor-PSJA Ludy Avila-STC Mahmoud Gassem-STC | Additional key partners identified and attended |
| Action | What | When | Where | How | Who | Outcome |
| 3. | Collect and report regional data to use in aligning decision making and follow up |  |  |  |  |  |
|  | Collect and report initial data from publicly available sites | 9/24/12 |  |  | Laura Saenz-UTPA | Powerpoint developed and submitted to AVATAR |
|  | Submit and certify PSJA data to THECB | 1/31/13 | PSJA |  | PSJA, UTPA & STC Laura Saenz-UTPA | Pathways reports provided by THECB |
| 4. | Create shared understandings | 1/9/13 | UTPA | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA Tim Sears-UTPA John Villarreal-UTPA Chris Smith- UTPA David Garza-PSJA Luis Suarez-PSJA Israel Nicanor-PSJA Ludy Avila-STC Mahmoud Gassem-STC | Developed shared understanding of alignment Identified key goals Identified data requests |
|  | -Create shared understandings -Train and introduce new members: Weslaco ISD and Region One | 3/1/13 |  | Face-to-face meeting | Laura Saenz-UTPA Daniel Plas-UTPA John Villarreal-UTPA Chris Smith- UTPA David Garza-PSJA Luis Suarez-PSJA Israel Nicanor-PSJA Wally Johnson –STC Ludy Avila-STC Patty Gandy – Region One, T-STEM Center Barbara Gonzalez-Region One Sergio Garcia-Weslaco ISD Connie Sinoy-Weslaco ISD Maria Castillo-Weslaco ISD Guest: Jay Bhat | Developed shared understanding of alignment Discussed key short term and long-term goals |
|  | -Create shared understandings -Train and introduce new members: Sharyland and McAllen ISD | 4/5/13 |  | Face-to-face meeting | Laura Saenz-UTPA Time Sears-UTPA John Villarreal-UTPA Chris Smith- UTPA Frank Dean - UTPA Wally Johnson-STC Mahmoud Gassem-STC Israel Nicanor-PSJA Patty Gandy – Region One, T-STEM Center Connie Sinoy-Weslaco Maria Castillo-Weslaco Graciela DeAnda-Sharyland Orlando Montalvo-Sharyland Ofelia Garza-Sharyland Oralia Arrellano – McAllen Gracie Padaca-McAllen Wendy Grohler-McAllen Marie Smith-McAllen | Developed shared understanding of alignment Discussed key short term and long-term goals |

| Action | What | When | Where | How | Who | What |
| --- | --- | --- | --- | --- | --- | --- |
| 5. | Determine goals |  |  |  |  |  |
|  | Short-term goals | Started: 1/9/13 and ongoing |  | Face-to-face meetings | All team members | -Develop exit/entry level assessments for chemistry courses at the secondary level -Examine the predictive power of Algebra II performance to post-secondary Chemistry performance -Develop self-assessments for teachers to become basis for professional development to be provided |
|  | Long-term goals | Started: 1/9/13 and ongoing |  | Face-to-face meetings | All team members | -Provide professional development to teachers -Bridge programs for students |